## 02. Impact Goal Overview - 7647
Goal ID | Impact Area | Goal Description | Impact Metric | Target Number | Midway Reporting (June 2025 - October 2025) | Endline Reporting (total June 2025-February 2026) | % of KPI Achieved | No longer Applicable | Later Stages --> | Onboarding Due Date | Midway Reporting Due Date | Endline Reporting Due Date | Onboarding Status | Midway Reporting Status | Endline Reporting Status | SUM: Reporting Status | Hidden --> | Level | Child | Status ID | Report | PS Cycle | Project Name | Fellow ID | Fellow Email | Fellow Full Name | VC Name | VC Email | VC Group | Cohort | Region
GOAL | [13 empty] | Outstanding | Outstanding |  |  | 1 |  | 0 |  | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe
| Environmental Impact | By March 30, 2026, we aim to eliminate the burning of about 100 kilograms of firewood. | metric tons of CO2 emissions reduced | 10 | 0 |  | 0% | TRUE |  |  |  |  | Outstanding | Outstanding | Outstanding |  |  | 2 | TRUE |  | GOAL | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe
| Project Growth | By December 2025, we will officially introduce our idea to a recognized organization, ensuring compliance and paving the way for broader adoption. | number of company registrations, patents secured or licenses aquired | 1 | 0 | 1 | 100% | [5 empty] | Outstanding | Outstanding | Outstanding |  |  | 2 | TRUE |  | GOAL | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe
| Social Impact | By December 2025, we will begin constructing a biodigester on a farm, as previously agreed upon with the landowner. | number of jobs created or experts hired | 1 | 1 | 5 | 500% | [5 empty] | Outstanding | Outstanding | Outstanding |  |  | 2 | TRUE |  | GOAL | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe
| Environmental Impact | By March 2025, the biodigester will be fully operational, producing biogas. | metric tons of CO2 emissions reduced | 1 | 0 | 2.61 | 261% | [5 empty] | Outstanding | Outstanding | Outstanding |  |  | 2 | TRUE |  | GOAL | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe
| Social Impact | By Feb 2025, conduct workshops, train locals to be the operators of the biodigester | number of people trained | 2 | 0 | 4 | 200% | [5 empty] | Outstanding | Outstanding | Outstanding |  |  | 2 | TRUE |  | GOAL | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe
| Environmental | By March 30, 2026, we aim to eliminate the burning of about 100 kilograms of firewood. | metric tons of CO2 emissions reduced | 1 |  | 2.64 | 264% | [5 empty] | Outstanding |  | Outstanding |  |  | 2 | TRUE |  | GOAL | Cycle 25-26 | BioViL | 7647 | pankajragmy@gmail.com | Pankaj Sharma | Mark Malhotra | mark.ext@thedoschool.org | C7 | Cohort 2 (2024/25) | Europe

## Comments
Row 2 | I believe there have been a mistake during the changes that were suppose to be made to the original Impact Metric, as mentioned in the previous comment. So this KPI is successfully achieved as mentioned below: GHGs generated due to burning of wood: 220.1 kg CO2e per month = 2641.2 kg/a Calculation totals (120 kg wood): CO2: 120×1.81 ≈ 120×1.81 ≈ 217.2 kg CO2.​ CH4: 120×0.14 g/kg ≈ 120×0.14 g/kg ≈ 16.8 g CH4 (0.0168 kg).​ N2O: 120×0.07 g/kg ≈ 120×0.07 g/kg ≈ 8.4 g N2O (0.0084 kg).​ CO2e using EPA GWPs (CH4=25, N2O=298): 217.2 + 0.0168 × 25 + 0.0084 × 298 ≈ 217.2 + 0.0168 × 25 + 0.0084 × 298 ≈ 220.1 kg CO2e. | pankajragmy@gmail.com | 02/21/26 7:30 AM
Row 2 | Since the target was thought as I initially applied for the Pioneer Scholarship, I would like to change the statement to: .....reduce burning of 100 kgs of firewood, which changes the target to 1 metric tonnes | pankajragmy@gmail.com | 06/30/25 12:50 PM
Row 3 | We have now officially registered BioViL in India. I have attached the registration certificate. Due to complications in registering the organisation to my name as I am a Non-Residing Indian (NRI), I decided to register the entity to my mother's name, keeping me as the other founder as the legality requires a residing Indian to be the core partner and then a NRI can be the other partner. This will be later changed as I find a suitable co-founder. | pankajragmy@gmail.com | 02/21/26 7:35 AM
Row 3 | I would change the month of this target to December | pankajragmy@gmail.com | 06/30/25 12:47 PM
Row 4 | We also employed 3 more people to construct the biodigester, so the exact achieved target increases to 4 including the previously hired intern for the website development. Along with it another intern is improving and enhancing the logo for the idea, with a proper storyline behind it and that increases the achieved number to 5 | pankajragmy@gmail.com | 01/02/26 8:37 AM
Row 4 | Hired an intern to develop a website for the project. The objective here was to go beyond basic website development to also make a youth capable of understanding how the market, technology, and the economy of bioenergy works, so a lot of the tasks were developed along the website development to make one youth familiar to the project and then later to also make them the grassroot drivers of the project in our community. Hence, the target number for this Impact Area is achieved. | pankajragmy@gmail.com | 10/28/25 7:07 AM
Row 4 | Similarly, as this target was based on my Pioneer Scholarship application, I would like to change the Description to: By December 2025 we will begin constructing a biodigester........ And, the target number to: 1 | pankajragmy@gmail.com | 06/30/25 12:53 PM
Row 5 | This KPI is also achieved as mentioned below: GHGs generated by unutilized, decomposing and ideal animal waste: 218 kg CO2e per month = 2616 kg/annum Calculated totals (600 kg, warm liquid/slurry, MCF=65%): CH4 volume per kg fresh waste: 0.13×0.24×0.65 ≈ 0.13×0.24×0.65 ≈ 0.0203 m³ CH4/kg. CH4 mass per kg fresh waste: 0.0203×0.7168 ≈ 0.0203×0.7168 ≈ 0.0145 kg CH4/kg (≈14.5 g/kg).​ Total CH4: 600×0.0145 ≈ 600×0.0145 ≈ 8.7 kg CH4.​ CO2e (using EPA’s CH4 GWP100=25 for consistency with the wood calculation): 8.7×25 ≈ 8.7×25 ≈ 218 kg CO2e. | pankajragmy@gmail.com | 02/21/26 7:31 AM
Row 5 | Similarly, this target was set while applying for the Pioneer Scholarship, the target number changes to 1 metric tonnes. | pankajragmy@gmail.com | 06/30/25 12:55 PM
Row 6 | We have conducted 3 workshops with the farm owner (4 individuals of the family). The first workshop was to educate the family about the concept of bioenergy solutions, alternative solutions to cattle waste, impact of using firewood on health, etc. The second workshop was to educate and bring the family in parallel with the construction and basic functioning of a fixed-dome biodigester The third workshop was regarding the operation and maintenance of the biodigester for proper biogas production and ways to enhance the overall efficiency of the system | pankajragmy@gmail.com | 01/02/26 8:44 AM
Sheet | I would change the target month to December. | pankajragmy@gmail.com | 06/30/25 10:43 AM